## 2-Week Roadmap
Day | Theme | Workstream | Priority | Task / Activity | Repo Area | Owner | Effort (hrs) | Dependency | Deliverable | Acceptance Criteria | Metric / Target | Status
1 | Baseline & Scope | Evaluation | P0 | Create a representative golden question set covering factual lookup, comparison, summarization, multi-document synthesis, follow-ups, ambiguous questions, PDF tables/figures, and timestamped video questions. | tests/, engine/app/rag/ | RAG Engineer | 4 | Access to representative PDFs/videos | Versioned evaluation dataset with expected evidence and answer notes | At least 60 questions; ≥10 video questions; ≥10 multi-document questions; each question has expected source IDs/pages/timestamps | 60+ labeled questions | Done
1 | Baseline & Scope | Observability | P0 | Instrument the existing question-to-response path and record stage timings, failures, provider, retrieval mode, token usage, and request correlation. | backend/app/api/main.py; backend/app/api/retrieval.py; engine/app/rag/ | Backend Engineer | 4 | Current request_id middleware | Baseline telemetry schema and local report | Every evaluation request exposes trace ID and timing for preparation, embedding, retrieval, reranking, generation, and persistence | ≥95% requests fully traced | Done
2 | Question Intelligence | Query Processing | P0 | Harden follow-up resolution, standalone-question rewriting, ambiguity detection, and clarification behavior using deterministic fallbacks. | engine/app/rag/answer.py; backend/app/api/main.py | RAG Engineer | 5 | Day 1 evaluation set | Improved query planning module plus unit tests | Follow-ups retain document/topic context; ambiguous requests ask one useful clarification; failures never silently alter intent | ≥90% query-plan accuracy | Done
2 | Question Intelligence | Security | P0 | Test guardrail behavior against prompt injection, requests to reveal system prompts, malicious content embedded in retrieved documents, and cross-document access attempts. | backend/app/security/; engine/app/rag/ | Backend Engineer | 3 | Representative attack set | Security regression tests and documented decisions | Blocked requests are audited; retrieved text is treated as untrusted data; authorized questions remain unaffected | 100% critical attacks blocked | Done
3 | Retrieval Quality | Retrieval | P0 | Normalize document/video filters and implement robust hybrid retrieval combining dense vector search and BM25 with reciprocal-rank fusion. | backend/app/api/retrieval.py; engine/app/rag/retriever.py | RAG Engineer | 6 | Compatible embeddings and indexed chunks | Single hybrid retrieval interface | Same behavior across providers; doc_id/source_type filters always apply; duplicate chunks are removed before context construction | Recall@10 ≥85% | Done
3 | Retrieval Quality | Testing | P0 | Add retrieval tests for PDF pages, tables, headings, multilingual queries, video timestamps, and no-match scenarios. | tests/; engine/app/rag/ | RAG Engineer | 2 | Hybrid retrieval interface | Automated retrieval regression suite | Tests run offline where possible and fail when expected evidence drops below configured rank | Top-5 hit rate ≥80% | Done
4 | Retrieval Quality | Reranking | P0 | Add configurable reranking after candidate retrieval, with lexical/model fallback and strict latency budget. | backend/app/api/retrieval.py; engine/app/rag/retriever.py | RAG Engineer | 5 | Day 3 candidates | Reranking stage with feature flag | Reranking improves evidence ranking on golden set and falls back safely when provider is unavailable | MRR improvement ≥10% | Done
4 | Retrieval Quality | Context Selection | P0 | Implement diversity-aware context selection, adjacent-chunk expansion, table preservation, and per-document/context token budgets. | engine/app/rag/answer.py; engine/app/schemas/chunk.py | RAG Engineer | 3 | Reranked candidates | Context builder v2 | Context stays within model limit; avoids redundant evidence; preserves page/timestamp metadata and table structure | Context duplication <15% | Done
5 | Grounded Generation | Prompting | P0 | Refactor answer prompt and structured output contract for insights, evidence, citations, uncertainty, and missing information. | engine/app/rag/answer.py; engine/app/rag/prompt_store.py; engine/app/prompts/ | RAG Engineer | 5 | Context builder v2 | Versioned production answer contract | Every material claim maps to retrieved evidence; model explicitly reports insufficient evidence; schema parsing has repair/fallback | Citation precision ≥95% | Done
5 | Grounded Generation | Citation Validation | P0 | Validate citations against retrieved chunk IDs, page numbers, and video timestamp ranges before returning a response. | engine/app/rag/answer.py; backend/app/api/retrieval.py | Backend Engineer | 3 | Structured answer contract | Citation validator and regression tests | Invalid or invented citations cannot reach the UI; unsupported claims lower confidence or trigger a constrained response | 0 fabricated source IDs | Done
6 | Reliability | Provider Resilience | P0 | Standardize timeouts, bounded retries with jitter, error classification, provider fallback, and circuit-breaker behavior for embedding/chat/reranking calls. | engine/app/clients/; backend/app/api/retrieval.py | Backend Engineer | 5 | Provider credentials/test doubles | Shared resilience policy | Transient failures retry; permanent failures fail fast; user receives consistent response; internal error retains trace ID | ≥99% graceful failure handling | Done
6 | Reliability | Caching | P1 | Review cache keys and add safe caching for query embeddings, retrieval results, and deterministic question preparation with versioned invalidation. | backend/app/api/retrieval.py; engine/app/clients/ | Backend Engineer | 3 | Stable model/index version identifiers | Cache policy and implementation | Keys include tenant/filter/provider/model/index versions; no cross-user or stale-index leakage | Repeat-query latency ↓30% | Done
7 | Performance | Latency & Cost | P0 | Profile the full path under concurrent load; optimize blocking I/O, thread usage, connection pooling, context size, and streaming time-to-first-token. | backend/app/api/main.py; backend/app/db/; engine/app/ | Backend Engineer | 5 | Day 1 telemetry | Performance profile and prioritized fixes | Streaming starts promptly; no unbounded workers; DB/model connections are reused safely | p95 <8s; TTFT <2.5s | In Progress
7 | Performance | Load Testing | P1 | Create load tests for chat, streaming, session history, mixed PDF/video filters, and degraded provider behavior. | tests/; scripts/ | QA/Backend | 3 | Stable test environment | Repeatable load-test scenario and report | System meets target concurrency without corrupt streams, exhausting pools, or mixing sessions | 20 concurrent users; error <2% | In Progress
8 | Production Quality | Evaluation | P0 | Build an automated evaluation runner for retrieval, groundedness, citation correctness, answer completeness, latency, and cost. | tests/; scripts/; engine/app/rag/ | RAG Engineer | 5 | Golden set and telemetry | Machine-readable evaluation report with baseline comparison | One command produces per-question results, aggregate metrics, and regression thresholds | All P0 thresholds reported | Done
8 | Production Quality | Confidence | P1 | Calibrate answer confidence using retrieval strength, evidence coverage, citation validation, and generation outcome instead of model self-confidence alone. | backend/app/api/retrieval.py; engine/app/rag/answer.py | RAG Engineer | 3 | Evaluation runner | Calibrated confidence policy | Low-evidence answers are labeled low confidence or withheld; high-confidence label correlates with correctness | High-confidence precision ≥90% | Done
9 | Hardening | End-to-End Tests | P0 | Run and fix end-to-end scenarios across OpenAI/Databricks modes, PDF/video filters, follow-ups, streaming fallback, provider failures, and authorization boundaries. | backend/; engine/; tests/ | Team | 5 | Days 2–8 changes | Passing E2E suite and defect log | No open critical defects; streaming and JSON responses are contract-compatible; source metadata renders correctly | 100% P0 E2E pass | In Progress
9 | Hardening | Operations | P1 | Define dashboards/alerts and operational runbooks for latency, errors, empty retrieval, low confidence, token cost, index/model mismatch, and provider outages. | deploy/; docs/; backend/app/api/ | Backend Engineer | 3 | Telemetry fields finalized | Production dashboard spec and runbook | Each alert has threshold, owner, diagnosis steps, and mitigation/rollback procedure | 100% critical alerts owned | In Progress
10 | Release | Regression & Release | P0 | Run the full evaluation and load suite, compare against Day 1 baseline, fix release blockers, and prepare a feature-flagged rollout. | Entire engine/backend path | Team | 5 | All prior tasks | Release candidate and go/no-go report | No P0 regression; quality and latency gates pass; rollback verified; known limitations documented | Quality + latency gates pass | In Progress
10 | Release | Knowledge Transfer | P1 | Document the final request lifecycle, configuration knobs, evaluation workflow, failure modes, and next-iteration backlog. | README.md; backend/README.md; engine/README.md; docs/ | RAG Engineer | 3 | Release candidate | Updated engineering documentation | A new engineer can run evaluation, interpret traces, change retrieval settings, and troubleshoot failures | Runbook walkthrough completed | In Progress

## Implementation Evidence
Area | Status | Implementation Evidence | Validation
User experience | Done | Technical engine stages are translated to seven plain-language SSE phases; technical detail remains in telemetry only. | UI production build and progress regression test pass.
Question intelligence | Done | Conversation rewrite, deterministic ambiguity fallback, clarification flow, and prompt-injection boundary. | Question-preparation and production-engine smoke tests pass.
Security | Done | Expanded deterministic attack handling plus untrusted-source prompt policy. | 13/13 versioned security regression cases pass.
Hybrid retrieval | Done | Provider-independent BM25 + semantic retrieval, reciprocal-rank fusion, filtering, deterministic reranking, optional model reranker. | 61-case retrieval suite passes release gates.
Context quality | Done | Near-duplicate removal, adjacent evidence, per-document diversity, table preservation, chunk and token budgets. | Context-selection regression tests pass.
Grounded generation | Done | Citation source/page/timestamp/text validation and evidence-calibrated confidence. | Document/video citation regression tests pass.
Reliability | Done | Timeouts, retries with jitter, circuit breaker, graceful lexical fallback, tenant-safe versioned cache. | Retry/circuit and cache-isolation tests pass.
Observability | Done | Trace IDs, per-stage latency, modes, cache/fallback/errors, token usage, rolling p50/p95 metrics. | Telemetry regression tests pass.
Evaluation | Done | Retrieval, end-to-end RAG, security, release-gate, and load-test runners. | Retrieval: hit 0.9836, expected-doc recall 0.9617, MRR 0.8405.
Live provider evaluation | Blocked externally | Runner is complete and handles per-case provider failures. | Configured OpenAI account returns 429 insufficient_quota.
Local load test | Blocked externally | Bounded concurrent load-test runner is complete. | Docker Desktop/API is not running in the current environment.
Release | Ready after external gates | All code, unit/smoke tests, UI build, documentation, alerts, and rollback instructions are complete. | Run live RAG and load gates before deployment.

## Daily Outcomes
Day | Primary Outcome | End-of-Day Demo / Evidence | Exit Gate
1 | A measurable baseline exists. | Baseline scores and trace for at least five representative questions. | Golden set schema approved and all pipeline stages measurable.
2 | Questions are interpreted safely and consistently. | Follow-up, ambiguous, injection, and access-boundary examples. | Query preparation tests pass with no critical security miss.
3 | Hybrid retrieval is deterministic and filter-safe. | Side-by-side lexical, vector, and fused rankings. | Recall@10 and filter tests meet target.
4 | Best evidence reaches the prompt within budget. | Reranking and context-selection comparison. | MRR improves without unacceptable latency.
5 | Answers are grounded and citations are trustworthy. | PDF page and video timestamp citation examples. | No invented source identifiers in evaluation run.
6 | Provider failures degrade predictably. | Timeout, retry, cache, and fallback fault injection. | No uncaught provider error reaches the user.
7 | Latency and concurrency behavior are understood. | Load-test trace and top bottleneck fixes. | p95/TTFT/error targets pass or have approved remediation.
8 | Quality can be evaluated automatically. | Single-command evaluation report and confidence calibration. | Regression thresholds run in CI/local automation.
9 | Release behavior is hardened end to end. | Full E2E suite plus operations drill. | Zero open P0 defects.
10 | A rollout-ready engine release is available. | Baseline-vs-candidate scorecard and rollback demonstration. | Go/no-go checklist approved.

## Success Metrics
Category | Metric | Baseline | 2-Week Target | How Measured | Release Gate | Owner
Retrieval | Recall@10 | Measure Day 1 | ≥85% | Expected evidence appears in top 10 | Yes | RAG Engineer
Retrieval | Top-5 evidence hit rate | Measure Day 1 | ≥80% | Expected evidence appears in top 5 | Yes | RAG Engineer
Retrieval | Mean Reciprocal Rank | Measure Day 1 | ≥10% improvement | Rank of first relevant chunk | Yes | RAG Engineer
Generation | Citation precision | Measure Day 1 | ≥95% | Cited source supports associated claim | Yes | RAG Engineer
Generation | Fabricated source IDs | Measure Day 1 | 0 | Validator rejects unknown chunk/page/timestamp references | Yes | Backend Engineer
Generation | Grounded-answer pass rate | Measure Day 1 | ≥90% | Human/LLM rubric checked against retrieved evidence | Yes | RAG Engineer
Confidence | High-confidence precision | Measure Day 1 | ≥90% | Correct answers among high-confidence responses | No | RAG Engineer
Latency | Time to first token p95 | Measure Day 1 | <2.5 sec | SSE request telemetry | Yes | Backend Engineer
Latency | End-to-end p95 | Measure Day 1 | <8 sec | Request start to final SSE event | Yes | Backend Engineer
Reliability | Chat error rate | Measure Day 1 | <2% | Load-test and production-like request outcomes | Yes | Backend Engineer
Reliability | Graceful provider failure | Measure Day 1 | ≥99% | Fault-injection scenarios produce controlled response | Yes | Backend Engineer
Scale | Concurrent users | Measure Day 1 | 20 | Mixed PDF/video load scenario | No | QA/Backend
Cost | Tokens/cost per answer | Measure Day 1 | No regression; target -15% | Provider usage fields by request | No | RAG Engineer
Operations | Fully traced requests | Measure Day 1 | ≥95% | Required stage fields present for request ID | Yes | Backend Engineer

## Backlog After 2 Weeks
Priority | Initiative | Why It Matters | Suggested Next Step | Status
P1 | Query decomposition for complex insight questions | Improves multi-hop and multi-document synthesis. | Evaluate planner on a separate complex-query set. | Deferred
P1 | Parent-child or hierarchical retrieval | Balances precise chunks with broader document context. | Prototype parent retrieval using existing section metadata. | Deferred
P1 | Document-level summaries and metadata filters | Improves broad corpus questions and routing. | Generate versioned summaries during ingestion. | Deferred
P1 | Multilingual retrieval evaluation | The enrichment pipeline already handles mixed Hindi-English content. | Create multilingual and code-switching golden questions. | Deferred
P1 | Online relevance feedback | Thumbs-up/down data can improve retrieval and prompt decisions. | Define privacy-safe feedback features and offline analysis. | Deferred
P2 | A/B testing framework | Enables evidence-based prompt/retrieval changes. | Add experiment assignment and metric attribution. | Deferred
P2 | Semantic answer cache | Can reduce latency and provider cost for equivalent questions. | Prototype tenant-safe similarity threshold and invalidation. | Deferred
P2 | Advanced video scene segmentation | May retrieve better evidence than fixed time windows. | Compare scene-aware chunks against current windows. | Deferred
P2 | Index migration/versioning workflow | Avoids downtime when embeddings or schemas change. | Add blue/green table aliases and compatibility checks. | Deferred

## Risks & Decisions
ID | Type | Risk / Decision | Impact | Mitigation / Decision Needed | Owner | Review Day | Status
R1 | Risk | Golden set is too small or not representative. | Optimizations overfit demos and regress real questions. | Sample actual PDF/video question patterns and reserve a blind holdout set. | Product + RAG | 1 | Not Started
R2 | Risk | Embedding model/index dimensions do not match across environments. | Vector retrieval fails or silently excludes chunks. | Record model, dimension, and index version; fail health check on mismatch. | Backend | 3 | Not Started
R3 | Risk | Provider differences create inconsistent behavior. | OpenAI and Databricks deployments produce different rankings/answers. | Use a shared response contract and provider-specific conformance tests. | RAG Engineer | 5 | Not Started
R4 | Risk | Reranking increases latency more than quality. | SLO regression. | Feature flag it, cap candidate count, enforce timeout, keep lexical fallback. | RAG Engineer | 4 | Not Started
R5 | Risk | Document content contains prompt injection. | Answer manipulation or data exposure. | Delimit retrieved content, prohibit following document instructions, add attack tests. | Security | 2 | Not Started
R6 | Risk | Two-week scope exceeds available engineering capacity. | Release remains partially hardened. | Protect P0 path; move P1 items to backlog when daily exit gates slip. | Tech Lead | 1 | Not Started
D1 | Decision | Primary production provider and fallback order. | Changes evaluation matrix, caching, error policy, and cost targets. | Confirm OpenAI vs Databricks primary by Day 1. | Tech Lead | 1 | Not Started
D2 | Decision | Target concurrency and latency SLO. | Determines load profile and acceptable reranking/context cost. | Confirm p95 and user concurrency targets by Day 1. | Product + Tech Lead | 1 | Not Started
D3 | Decision | What qualifies as an acceptable insufficient-evidence answer. | Controls hallucination/coverage tradeoff. | Approve response wording and confidence policy by Day 5. | Product | 5 | Not Started

## Assumptions & Usage
RAG Engine — Two-Week Production Improvement Plan
Plan window | 10 business days / 2 working weeks
Scope | Incoming question → security and question preparation → retrieval/reranking → context construction → answer generation/citations → streaming/persistence/observability.
Primary assumption | One primary RAG/backend engineer, with part-time QA/security/product review. Parallelize tasks when additional engineers are available.
Out of scope | Major ingestion redesign, frontend redesign, infrastructure migration, and model fine-tuning. Relevant follow-on items are kept in the backlog.
How to use | Update Status in the roadmap daily. Treat P0 tasks and release gates as mandatory. Record Day 1 baselines in Success Metrics, then compare the Day 10 candidate.
Daily cadence | 15-minute kickoff; focused implementation; end-of-day demo against the stated exit gate; log blockers in Risks & Decisions.
Release rule | Do not ship when a required release gate regresses, critical security tests fail, fabricated citations are possible, or rollback has not been verified.